{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Procedurat","Blerjet e  vogla"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":31,"defined_names":826,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Procedurat","index":0,"n_rows":12,"n_cols":9,"rows_kept":12,"cut":false,"hidden":true,"merged":[]}
["Nr.","Kodet CPV","Grupi i Spec. Teknike","Fondi Limit","Vlera e Kontratës","Mbikqyrje+Kolaudim","Situacion pjesor 1+2","Operatori Ekonomik Fitues","Operatori Ekonomik i shpallur fitues"]
[1,"Studim I Fisibilitetit  dhe Projekt Ideja per lidhjen hekurudhore Durres-Prishtine","1. Margarita Kodra\n2. Sokol Popoci\n3. Mentor Bunguri\n4. Petraq Pando               5. Alvarita Goga",200224996,73000000,null,null,null,"Bashkimi i Operatorëve Ekonomike ILF Consulting Engineers Austria GmbH & ABKONS SH.P.K "]
[2," RIPARIM (RINDERTIM) VEPRA ARTI (URA, TOMBINO ETJ)","UKD",64567889,75016884,"1077499.2+50667.6 = 1128166.8",32064260.59,"START&CO  ","START & CO"]
[3,"Paisje zyre per DP Hekurudhave ( Modernizimi I salles mbledhjes) ","Z.Hajri Molla        Zj.Andia Gjyli   Z.Alvarita Goga",2490420,2863200,null,null,"ATOM","ATOM"]
[4,"Paisje zyre per DP Hekurudhave ","Z.Gani Hoxha  Z.Maksim Prifti Z.Alvarita Goga",2470450,2090436,null,null,"SHAGA.","SHAGA"]
[5,"Hartim I planeve te rilevimit te truallit te stacioneve, linjave kryesore dhe degezimeve Hekurudhore","Z.Agim Kopani      Z.Vasil Gjoni         Z.Shpetim Bardhi",35000000,15000000]
[6,"RINOVIM I TRUNGUT HEKURUDHOR DURRES - ELBASAN (km 00+000 – 75+000)","Z. Petraq Pando         Zj.Margarita Kodra    Z.Ledion Subashi      ",50000000,51517185.600000001,"790533.6+48000=838533.6",null,"BEIS & SHKELQIMI 07","BE-IS shpk"]
[7,"RINOVIM I TRUNGUT HEKURUDHOR RROGOZHINE - LUSHNJE (km 35+300 – 52+350)","Z. Petraq Pando         Zj.Margarita Kodra    Z.Ledion Subashi      ",49958598.200000003,52448152,"789343.2+48000= 837343.2",null,"BEQIRI sh.p.k","BEQIRI"]
[8,"Makineri paisje per mirembajtjen e linjes hekurudhore"," Z.Ledion Subashi \n Z.Shpetim Bardhaj\n Z.Hiqmet Xhaferri\n",32000000,38136000,null,38136000,"POWER INDUSTRIES","POWER INDUSTRIES"]
[9,"Blerje mjete automobilistike "," Z.Fation Vokshi        Z.Klevis Kolorija     Z.Brunildo Durmisha",13080000,15465600,null,15465600,"“DESION” shpk","DESION"]
[10,"BLERJE PJESE KEMBIMI DHE AGREGATE PER LOKOMOTIVA DHE VAGONE","Z.Krenar Hasanaj             Z.Maksim Prifti    Z.Jurgen Tabaku",12498600,11432400,null,null,"ZEQIRI SHPK","Zeqiri"]
[11,"Rikonstruksion I tualeteve prane zyrave te drejtorise Hekurudha Shqiptare dhe riparim I parapetit","Zj. Margarita Kodra      Z.Brunildo durmishaj   Z.Klevis Kolorija  ",1551837,1228635,"26548+10193 = 36741",null,"Martin Konstruksion shpk","MARTINI KONSTRUKSION&REAL ESTATE"]

{"sheet":"Blerjet e  vogla","index":1,"n_rows":12,"n_cols":15,"rows_kept":12,"cut":false,"hidden":false,"merged":[]}
["Nr.","Emertesa e procedures","NJESIA qe ka bere kerkesen","Grupi i Spec. Teknike","Statusi hartimit  Specifikimet Teknike","Grupi i Fondit Limit ","Statusi  hartimit   Fondi Limit","Urdher Prokurimi","Kriteret Teknike/ftesa per ofert ","Data e Hedhjes ne Sistem","Data e Hapjes se Ofertave","Vlera e Kontratës","Operatori Ekonomik Fitues","Statusi I dorezimit te Mallrave apo Sherbimeve","Shenime te ndryshme "]
[1,"Blerje Pjesë Këmbimi Mjeti Lefterak NJSHML","NJSHML","J. Tabaku             A. Brjka            I. Leka","hartuar","L. Diko                 A. Goga             Sh. Veli","hartuar","nr. 59/2                          dt. 01/11/2023",null,"30/11/2023","04/12/2023","116.400 LEK",null,"Ne proces"]
[2,"Instrumenta matëse","NJBMIH","G. Hoxha             O. Gjura           L. Subashi","hartuar","L. Diko                 A. Goga             Sh. Veli","hartuar","nr. 70/1                          dt. 18/10/2023",null,"03/11/2023","07/11/2023","19,500 LEK","Entela Veliu","PERFUNDUAR"]
[3,"Riparimi i mjeteve të Mirëmbajtjes të Sektorit Logjistik","NJBMIH","G. Hoxha             O. Gjura           L. Subashi","hartuar","L. Diko                 A. Goga             Sh. Veli","hartuar","nr. 71/1                          dt. 18/10/2023",null,"18/10/2023","23/10/2023","755.000 LEK","SOKOL RROKAJ ","PERFUNDUAR"]
[4,"Mbikqyrje punimesh për objektin ”Rinovim i trungut hekurudhor Rrogozhinë - Lushnje ( km 37+450 – km 39+500 dhe km 48+850 – km 50+850 )","NJQ","L. Diko                 A. Goga             Sh. Veli","hartuar","L. Diko                 A. Goga             Sh. Veli","hartuar","nr. 20/5                          dt. 24/10/2023",null,"25/10/2023","27/10/2023","657.786,61 LEK","G & L CONSTRUCTION ","Ne proces","LIDHUR KONTRATA"]
[5,"Mbikqyrje punimesh për objektin ”Rinovim i trungut hekurudhor Durrës-Elbasan ( km 13+400 –   km 14+400; km 14+970 – km 15+970; km 39+500 – km 40+500 dhe km 56+000 – km 57+000 )","NJQ","L. Diko                 A. Goga             Sh. Veli","hartuar","L. Diko                 A. Goga             Sh. Veli","hartuar","nr. 21/3                          dt. 24/10/2023",null,"27/10/2023","31/10/2023","658,777.95 LEK","ELITE STUDIO","Ne proces","LIDHUR KONTRATA"]
[6,"Prishje muri dhe Zhvendosje/Mbulimi ne magazinen e NJSHML","NJBMIH","L. Diko                 A. Goga             Sh. Veli","hartuar","L. Diko                 A. Goga             Sh. Veli","hartuar","nr. 800/2                          dt. 02/11/2023",null,"03/11/2023","07/11/2023","71,450 LEK",null,null,"ASNJE OPERATOR EKONOMIK Pjesmarres"]
[7,"Blerje materiale per lyerjen e vagonave udhetar ","NJSHML","L. Diko                 A. Goga             Sh. Veli","hartuar","L. Diko                 A. Goga             Sh. Veli","hartuar","nr. 73/1                          dt. 01/11/2023",null,"03/11/2023","07/11/2023","159,160 LEK","ALMA KODRA","PERFUNDUAR"]
[8,"Blerje benzine ","NJQ","L. Diko                 A. Goga             Sh. Veli","hartuar","L. Diko                 A. Goga             Sh. Veli","hartuar","nr. 78                          dt. 15/11/2023",null,"16/11/2023","20/11/2023","332,000 LEK","D&J","PERFUNDUAR"]
[9,"Siguracione për mjetet DR 0975 D, DR 4584 D dhe DR 6902 B","NJBMIH","L. Diko                 A. Goga             Sh. Veli","hartuar","L. Diko                 A. Goga             Sh. Veli","hartuar","nr. 75/1                          dt. 03/11/2023",null,"17/11/2023","21/11/2023","98,998 LEK","ANSIG","PERFUNDUAR"]
[10,"Blerje fotokopje/printer A4 dhe A3 me ngjyra","PIU","L. Diko                 A. Goga             Sh. Veli","hartuar","L. Diko                 A. Goga             Sh. Veli","hartuar","nr. 82                          dt. 24/11/2023",null,"30/11/2023","04/12/2023","150,000 LEK",null,"Ne proces"]
[11,"Blerje materiale elektrike për HSH sha ","NJQ","L. Diko                 A. Goga             Sh. Veli","hartuar","L. Diko                 A. Goga             Sh. Veli","hartuar","nr. 81                          dt. 22/11/2023",null,"30/11/2023","04/12/2023","16,800 LEK",null,"Ne proces"]